## 1. Dashboard & Jun-26
SHEET 1 - FUND DASHBOARD & JUNE 2026 RESTATEMENT
Konigstein Affordable Housing Fund (KAHF) — GIPF 99.01% / Konigstein Capital 0.99%. All amounts N$ (NAD). Blue = source figure typed from a named document. Black = formula. Green = link to another tab in this workbook.
A. CAPITAL FROM GIPF — the input side
Total capital allocation approved for investment (fund level) | 446420000 | Fund drawdown register (KAHF_Damask Performance (CHQ) > Drawdowns), row 23 column P.
GIPF capital account at 31 July 2026 | 188072936 | KAHF trial balance as at 28-02-2026, account 5100/020.
GIPF capital account at 28 Feb 2025 (comparative) | 108341357 | Same trial balance, prior-year column. NOTE: a second trial balance in the pack shows N$131,984,039 at the same date — unreconciled.
Konigstein Capital capital account at 28 Feb 2026 | 1518374 | Account 5100/030. GIPF share of paid-in capital = 99.01%.
Movement in GIPF capital, Feb-25 to Jul-26 | 79731579 | Capital called from GIPF during the year.
Capital still callable from GIPF (undrawn) | 251902599.94 | Fund drawdown register row 106. Fund total N$254,421,625.91 of which KC N$2,519,025.97.
Management fees charged to the fund, inception to date | 46051257.45 | Fund drawdown register row 102.
Trust expenses, inception to date | 2748719.45 | Fund drawdown register row 103.
B. DISTRIBUTIONS TO GIPF — the output side
Cash distributions paid out of KAHF to GIPF, inception to date | 0 | NO distribution to GIPF is recorded anywhere in the Fund Model folder. The GIPF capital account shows contributions only, with no drawings. Every "distribution" in this model is a repayment from a project INTO the fund, available for recycling.
Project repayments received into the fund, inception to date | 207800002.09 | Sheet 2 portfolio total — ties to the Ledger and to Sheet 4.
of which recycled into new projects or held as fund liquidity | 207800002.09 | All project repayments have been redeployed or are held in fund liquidity — none has left the fund.
Fund liquidity — Capricorn High Yield Fund at 31 Jul 2026 | 53519717.75 | CAM investment statement, client 13853366, period 01-31 Jul 2026 (statement dated 11-08-2026).
Fund liquidity — Bank Windhoek current account at 28 Feb 2026 | 6109913.56 | KAHF trial balance 28-02-2026, account 8400/000.
Interest earned on fund liquidity, Jul 2026 | 343457.63 | CAM Interest July 2026 tab, KAHF - Interest Schedule July 2026.
C. BASELINE PERFORMANCE AS AT 30 JUNE 2026
Capital deployed into projects, inception to 30-Jun-26 | -352387510.42 | SUMIFS over the Ledger tab, date on or before 30-06-2026.
Distributions received from projects, inception to 30-Jun-26 | 207800002.09
Net capital outstanding at 30-Jun-26 | -144587508.33
Portfolio carrying value / NAV at the June-26 baseline | 117696377.76 | Sum of the carrying values on Sheet 2 — see that tab for the valuation date behind each one.
Cash Available | 67037158.71
Total value to the fund (distributions + NAV + Cash) | 392533538.56
TVPI on capital deployed at 30-Jun-26 | 1.1139
Net gain / (deficit) over capital deployed | 40146028.14
Interest earned across the loan book, Jan-Jul 2026 | 14897942.37 | KAHF - Interest Schedule July 2026, "Interest July 2026" tab, total column J.
D. PORTFOLIO SHAPE AT THE REPORTING DATE
Projects in the pack | 14 | Sheet 2 — 10 active, 4 completed.
Completed / fully redeemed projects | 4 | Heavens Ark, NIC Otjomuise Ext 10, Duma Tau, LIH Nkurenkuru Ph 1.
Total planned units across the portfolio | 6019 | Sheet 3 portfolio total.
Units delivered to date (where the pack records a count) | 200 | Blanks on Sheet 3 are unrecorded, not zero.
Reading this sheet: The whole of section D is one quarter — Jul to Sep 2026 — and it is dominated by two repayments.
The single most important disclosure on this page is line B (row 16).
D. RESTATEMENT — movements since the June 2026 baseline
Capital deployed after 30-Jun-26 | -11616720.46 | Tama Estates Phase 1 N$4,466,720 and PAM Tree notice 089 N$4,150,000, plus C-Breeze / Tama fee offsets.
Distributions received after 30-Jun-26 | 0 | PAM Tree N$28,390,200 and Turnstone Villas N$14,000,000 — the single largest repayment quarter in the fund's history.
Net movement since the baseline | -11616720.46
Restated capital deployed, inception to date | -371004230.88
Restated distributions received, inception to date | 207800002.09
Restated net capital outstanding | -163204228.79
Restated TVPI | 0.93197

## 2. Project Performance
SHEET 2 — PROJECT-BY-PROJECT PERFORMANCE
Every project in the Fund Model folder. Capital deployed and distributed are SUMIFS over the Ledger tab.
Project | Status | Capital deployed (N$) | Capital distributed (N$) | Net cash position (N$) | Approved deal size / facility (N$) | Total project cost (N$) | Gross development value (N$) | Carrying value / NAV (N$) | Total value (dist. + NAV) | MOIC / TVPI | Updated IRR | IRR basis and source
Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | Active | -95611595 | 37033391.08 | -58578203.92 | 63500000 |  |  | 40105521 | 77138912.08 | 0.80679 | 5.41% | Return Dashboard C8 — realised XIRR. Snapshot 'Expected IRR' on Contract Parameters K103 = 4.0%.
Damask Dunescape Villas | Completed | -25551000 | 24000000 | -1551000 | 39000000 |  |  | 12958884 | 36958884 | 1.4465 | 36.03% | Historical Ledgers F30 — XIRR incl. NAV N$8,508,452 and PM fees N$7,177,927.
PAM Tree Investment Pty Ltd - Kuisebmund Erf 5758 | Active | -45000000 | 0 | -45000000 | 45000000 |  |  | 35672548 | 35672548 | 0.79272 | 24% | Contract Parameters D31 — reported/projected. Workbook XIRR cell is broken (REF-error / mis-summed -33.5%).
Mossy Wood Notes Investments- Turnstone Villas | Completed | -16300000 | 0 | -16300000 | 16300000 |  |  | 4911828 | 4911828 | 0.30134 | -10.6% | Return Dashboard D19 — realised XIRR, event-dated, unrealised NAV excluded.
Lithon Developers - Nkurenkuru Ext 2 | Active | -5500000 | 0 | -5500000 | 5500000 |  |  | 1037365.93 | 1037365.93 | 0.18861 | 30.11% | Historical Ledgers D111 — IRR incl. terminal NAV. Cash-only realised IRR = 15.76% (D110). The 16.08% on the Return Dashboard is the effective annual rate of the 15% NACM coupon, not an IRR.
Damask- Mondesa Palms | Active | -15000000 | 0 | -15000000 | 28000000 | 31277883.81 | 42400000 | 12958884 | 12958884 | 0.86393 | 18.94% | Dashboard E9 — realised IRR base case. PROVISIONAL: facility size, rate, first-draw date and unit price are all placeholders.
Blue Mont Pty Ltd The Ridge | Active | -20000000 | 0 | -20000000 | 30000000 | 27926209.01 | 38000000 | 13022185.55 | 13022185.55 | 0.65111 | 18.53% | Dashboard E9 — realised IRR base case.
Mango Cove - Otjomuise Ext 10 | Active | -12000000 | 0 | -12000000 | 20000000 |  |  | 4827160 | 4827160 | 0.40226 | n/a | No IRR in the pack. Interest schedule prices the loan at 14.0% NACM.
Block 9 - C-Breeze Heights | Active | -4389111.14 | 0 | -4389111.14 | 5000000 | 26748597 | 31785000 | 4822787.04 | 4822787.04 | 1.0988 | 18% | Vert Development Model — 'Equity - Mezzanine' levered IRR (per instruction). Interest schedule: 15.37% base, 18.0% after participation top-up.
Block 9- Tama Estates | Active | -4466720.46 | 0 | -4466720.46 | 11000000 | 113500309 | 127130303 | 5249926.24 | 5249926.24 | 1.1753 | 20.8% | Vert Development Model — 'Equity - Investor' levered IRR (per instruction). Interest schedule XIRR on Phase-1 drawn capital = 18.35%.
Duma Tau — Kronlein | Completed | -36109399.24 | 42507267.9 | 6397868.66 | 28000000 |  |  | 1197995 | 43705262.9 | 1.2104 | 12.89% | Return Dashboard D19 — event-dated XIRR. Supersedes 11.69% and 15.86% previously reported.
LIH- Nkurenkuru Ph 1 | Completed | -19076405.04 | 21306075.5 | 2229670.46 | 18000000 |  |  | 1197968.19 | 22504043.69 | 1.1797 | 10.98% | Return Dashboard D19 — XIRR off Net LP cash flow.
NIC - Otjomuise Ext 10 | Completed | -7000000 | 7353424.49 | 353424.49 | 7000000 |  |  | 0 | 7353424.49 | 1.0505 | 17.91% | Return Dashboard D19 — realised XIRR, facility fully redeemed 28-Apr-23.
MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | Completed | -65000000 | 75599843.12 | 10599843.12 | 65000000 |  |  | 0 | 75599843.12 | 1.1631 | 18.57% | Return Dashboard D19 — XIRR off Net LP cash flow, fully redeemed.
PORTFOLIO TOTAL |  | -371004230.88 | 207800002.09 | -163204228.79 | 381300000 | 199452998.82 | 239315303 | 137963052.95 | 345763055.04 | 0.93197 | 18.67%
Note on B5: Distressed

## 3. Delivery Outputs
SHEET 3 — DELIVERY OUTPUTS (units built vs planned)
Planned units for the six named projects are hardcoded per instruction (blue). Every other figure is read from the project model named in the last column. Blank = the pack records no figure — do not read blank as zero.
Project | Total planned units | Erven / scope | Units built to date | Units sold / transferred | % complete | Units outstanding | Delivery status | Source in the model pack
A. ACTIVE PROJECTS — planned units hardcoded per instruction
PAM Tree (Erf 5758) | 189 | Erf 5758 Kuisebmund, Walvis Bay — 219 plots on the General Plan |  | 16 |  |  | Phase 1 of 3 under way | Contract Parameters D26 (219 plots), D28 (16 units sold). No units-built count is recorded in the workbook.
C-Breeze Heights | 13 | Erf 1329, CBD Swakopmund — single erf | 0 | 0 |  | 13 | Vertical construction Feb-26 to Oct-26 | Vert Development Model p.1 — 13 units, vertical end Oct-2026, transfers end Dec-2026. No completions recorded.
Tama Estates | 87 | Erf 673 Tamariskia — 8 stages | 0 | 0 |  | 87 | Horizontal from Apr-26; vertical from Jul-26 | Vert Development Model p.1 — 87 units, vertical start Jul-2026, transfers start Nov-2026.
Mondesa Palms | 134 | 134 units across 3 erven (4420 / 4421 / 4422) | 0 | 0 | 15% | 134 | Erf 4420 (40 units) in construction | Programme F7 — 15% complete at 18-Jun-26; practical completion forecast 09-Feb-27. Model covers Erf 4420 only.
The Ridge — Rocky Crest Ext 4 | 38 | Erf R/E 1502 & Erf 1757, Rocky Crest Ext 4 | 0 | 0 |  | 38 | Foundations from Jun-26 | BudgetActual D6 — construction actual N$0 against a N$20.0m budget; practical completion 01-Mar-27.
Mango Cove (Otjomuise Ext 10) | 109 | 109 units across 6 erven | 0 |  |  | 109 | Early drawdown stage | No delivery data in the pack. Unit count taken from the KAHF Projects schedule.
Sub-total — hardcoded plan | 570 |  | 0 | 16 |  | 570
B. OTHER PROJECTS IN THE PACK — planned units read from the models
Erf 1470 Khomasdal | 255 | 6 erven; 135 units to be delivered via KAHF (N$27.13m) + FNB (N$20m) | 93 |  | 41% | 162 | Phase 2 (Erf 7077, 24 units) under way | Contract Parameters C29 (93 constructed), C30 (255 to be constructed), K96 (229 housing units), K102 (41% complete). The three unit counts in this workbook do not agree.
Dunescape Villas (Erf 5159) | 40 | Erf R/E 5159 Ext 15, Swakopmund | 40 | 40 | 100% | 0 | Complete — all units sold and transferred | Cashflow B48 — 100% complete, all 40 units sold and transferred at 30-Apr-26. Contract Parameters M91 flags only 13 units traceable to a transfer schedule.
Turnstone Villas (Erf 8939) | 17 | Erf 8939 Ext 35, Swakopmund | 17 | 13 | 100% | 0 | Construction complete 09-Oct-25 | Contract Parameters E97 — construction complete, 13 of 17 transferred, all 17 sold; B112 — 4 sold not yet transferred.
Lithon Nkurenkuru Ext 2 | 37 | Erf 845, Nkurenkuru Ext 2 — Phase 2 | 33 |  | 89% | 4 | 33 of 37 houses complete at 30-Sep-25 | Cashflow C60/C61/C62 — 37 planned, 33 completed, 89.19% per the fund dashboard.
NIC Otjomuise Ext 10 (Erf 5221) | 17 | Erf 5221, Otjomuise Ext 10, Windhoek | 17 | 17 | 100% | 0 | Completed — facility redeemed Apr-23 | Contract Parameters D20 — 17 sectional title units. B122 flags units sold as not evidenced.
Sub-total — other projects | 366 |  | #REF! | #REF! |  | #REF!
C. PIPELINE PROJECTS
Ongwediva Town Council | 208 | [6 empty] | Kahf Projects Update
Karibib Town Council | 659 | [6 empty] | Kahf Projects Update
Goreangab - Waterfront | 815 | [6 empty] | Kahf Projects Update
Portion 156 Rundu (Kaisosi Ext 17) | 309 | [6 empty] | Kahf Projects Update
Karibi - Nasunga | 84 | [6 empty] | Kahf Projects Update
Universitas (Unam) Afrideca | 722
Auas View | 85
Abigail | 2201
Sub-total — other projects | 5083 |  | 200 | 70 |  | 4883
PORTFOLIO TOTAL | 6019 |  | 200 | 86 |  | 5819
Blue = hardcoded planned units supplied by the user. Green = figure read from the project model. Black = formula.
Variances against the hardcoded plan, for the record: Mondesa Palms — the model covers Erf 4420 (40 units) only, and the KAHF Projects schedule shows 131, not 134. The Ridge — the KAHF Projects schedule shows 40 units, not 38. PAM Tree, Mango Cove, C-Breeze and Tama agree with the schedule.
Erf 1470 Khomasdal carries three unit counts in one workbook (93 built, 255 to be constructed, 229 housing units, 135 across 6 erven). Treat the delivery number as unaudited until the developer confirms.

## 4. Monthly Cash Flows
SHEET 4 — CONSOLIDATED MONTHLY CASH FLOWS
Live tracking ledger. Every cell is a SUMIFS over the Ledger tab, so adding a dated row on Ledger updates this sheet, Sheet 2 and Sheet 1 automatically. Deployments negative, distributions positive. N$ (NAD).
Month | Fund drawdowns | Fund distributions | Net movement | Cumulative net position | Erf 1470 Khomasdal | Dunescape Villas (Erf 5159) | PAM Tree (Erf 5758) | Turnstone Villas (Erf 8939) | Lithon Nkurenkuru Ext 2 | Mondesa Palms | The Ridge — Rocky Crest Ext 4 | Mango Cove (Otjomuise Ext 10) | C-Breeze Heights | Tama Estates | Duma Tau — Kronlein | LIH Nkurenkuru Ph 1 | NIC Otjomuise Ext 10 (Erf 5221) | Heavens Ark — Otjomuise
2017-11-01 | -47700000 | 0 | -47700000 | -47700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-03-01 | -22000000 | 0 | -22000000 | -22000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22000000 | 0 | 0 | 0
2018-04-01 | -10000000 | 0 | -10000000 | -10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-06-01 | -700000 | 0 | -700000 | -700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-07-01 | -4300000 | 0 | -4300000 | -4300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-08-01 | -11000000 | 0 | -11000000 | -11000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6000000 | 0 | 0 | 0
2018-09-01 | -2500000 | 1302000 | -1198000 | -1198000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1302000 | 0 | 0 | 0
2018-10-01 | -10000000 | 0 | -10000000 | -10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-11-01 | -11600000 | 0 | -11600000 | -11600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-12-01 | 0 | 10443745 | 10443745 | 10443745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10443745 | 0 | 0 | 0
2019-01-01 | -12450000 | 4425225 | -8024775 | -8024775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4425225 | 0 | 0 | 0
2019-02-01 | -10400000 | 3242310 | -7157690 | -7157690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3242310 | 0 | 0 | 0
2019-03-01 | -14200000 | 4087330 | -10112670 | -10112670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4087330 | 0 | 0 | 0
2019-04-01 | 0 | 1923105 | 1923105 | 1923105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1923105 | 0 | 0 | 0
2019-05-01 | -4000000 | 1678090.04 | -2321909.96 | -2321909.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 679120 | 0 | 0 | 0
2019-06-01 | -4268344.28 | 5417251.28 | 1148907 | 1148907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -823394.24 | 0 | 0 | 0
2019-07-01 | -3450000 | 450000 | -3000000 | -3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1550000 | 0 | 0 | 0
2019-09-01 | -4123595 | 4123594.94 | -0.06 | -0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3269720 | 0 | 0 | 0
2019-10-01 | -1917460 | 5945790.17 | 4028330.17 | 4028330.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1917460 | 0 | 0 | 0
2019-12-01 | -1000000 | 38288179.11 | 37288179.11 | 37288179.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1000000 | 0 | 0 | 0
2020-01-01 | 0 | 8227944.32 | 8227944.32 | 8227944.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-03-01 | -7000000 | 22312884.03 | 15312884.03 | 15312884.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-09-01 | 0 | 7609365.83 | 7609365.83 | 7609365.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-10-01 | 0 | 948648 | 948648 | 948648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-03-01 | 0 | 11994122.64 | 11994122.64 | 11994122.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3798648.74 | 0 | 0 | 0
2021-04-01 | 0 | 11099288.4 | 11099288.4 | 11099288.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-07-01 | 0 | 9476082 | 9476082 | 9476082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-09-01 | 0 | 10117520.5 | 10117520.5 | 10117520.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1152462.5 | 0 | 0 | 0
2021-11-01 | 0 | 7613174.52 | 7613174.52 | 7613174.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 737907.5 | 0 | 0 | 0
2021-12-01 | 0 | 4575267.76 | 4575267.76 | 4575267.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3481490.1 | 0 | 0 | 0
2022-05-01 | -5500000 | 0 | -5500000 | -924732.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2022-08-01 | -7000000 | 0 | -7000000 | -7000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2022-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2022-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-01 | 0 | 6983276.26 | 6983276.26 | 6983276.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 694476.87 | 0 | 0 | 0
2023-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-01 | 0 | 1515807.29 | 1515807.29 | 1515807.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 451182.19 | 0 | 0 | 0
2023-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-08-01 | -6000000 | 0 | -6000000 | -6000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-10-01 | -2500000 | 0 | -2500000 | -2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-11-01 | -4675000 | 0 | -4675000 | -4675000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2024-03-01 | -5000000 | 0 | -5000000 | -5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2024-06-01 | -3600000 | 0 | -3600000 | -3600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2024-08-01 | -8000000 | 0 | -8000000 | -8000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2024-09-01 | -9751000 | 0 | -9751000 | -9751000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2024-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2024-11-01 | -7413000 | 0 | -7413000 | -7413000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2024-12-01 | -18200000 | 0 | -18200000 | -18200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-02-01 | -10100000 | 0 | -10100000 | -10100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-01 | -3640000 | 0 | -3640000 | -3640000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-01 | -7400000 | 0 | -7400000 | -7400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-01 | -20000000 | 0 | -20000000 | -20000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-01 | -12000000 | 24000000 | 12000000 | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-01 | -2260000 | 0 | -2260000 | -2260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-01 | -10750000 | 0 | -10750000 | -10750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-01 | -13600000 | 0 | -13600000 | -13600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-01 | -1209348.2 | 0 | -1209348.2 | -1209348.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-01 | -11179762.94 | 0 | -11179762.94 | -11179762.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-01 | -11616720.46 | 0 | -11616720.46 | -11616720.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-01 | -7000000 | 0 | -7000000 | -7000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | -371004230.88 | 207800002.09 | -163204228.79 | -7000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6397868.66 | 0 | 0 | 0
Control: row totals tie to Ledger row 163 and to Sheet 2 column C/D.

## Ledger
CONSOLIDATED EVENT LEDGER — every dated fund cash flow behind Sheets 1-4
Fund perspective: capital deployed shown negative, distributions received positive. All amounts N$ (NAD). Blue = source figure typed from a model; nothing on this tab is derived.
Date | Project | Amount (N$) | Drawdown (N$) | Distribution (N$) | Month key | Source workbook / tab
2017-11-28 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -45500000 | -45500000 | 0 | 2017-11-01 | Drawdown Register
2017-11-28 | LIH- Nkurenkuru Ph 1 | -2200000 | -2200000 | 0 | 2017-11-01 | Drawdown Register
2018-03-09 | Duma Tau — Kronlein | -22000000 | -22000000 | 0 | 2018-03-01 | Drawdown Register
2018-04-26 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | -10000000 | -10000000 | 0 | 2018-04-01 | Drawdown Register
2018-06-29 | LIH- Nkurenkuru Ph 1 | -700000 | -700000 | 0 | 2018-06-01 | Drawdown Register
2018-07-23 | LIH- Nkurenkuru Ph 1 | -4300000 | -4300000 | 0 | 2018-07-01 | Drawdown Register
2018-08-10 | Duma Tau — Kronlein | -6000000 | -6000000 | 0 | 2018-08-01 | Drawdown Register
2018-08-10 | LIH- Nkurenkuru Ph 1 | -5000000 | -5000000 | 0 | 2018-08-01 | Drawdown Register
2018-09-13 | Duma Tau — Kronlein | 1302000 | 0 | 1302000 | 2018-09-01 | Drawdown Register
2018-09-19 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -1500000 | -1500000 | 0 | 2018-09-01 | Drawdown Register
2018-09-19 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | -1000000 | -1000000 | 0 | 2018-09-01 | Drawdown Register
2018-10-11 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | -10000000 | -10000000 | 0 | 2018-10-01 | Drawdown Register
2018-11-22 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | -9400000 | -9400000 | 0 | 2018-11-01 | Drawdown Register
2018-11-29 | LIH- Nkurenkuru Ph 1 | -2200000 | -2200000 | 0 | 2018-11-01 | Drawdown Register
2018-12-14 | Duma Tau — Kronlein | 10443745 | 0 | 10443745 | 2018-12-01 | Drawdown Register
2019-01-11 | Duma Tau — Kronlein | 4425225 | 0 | 4425225 | 2019-01-01 | Drawdown Register
2019-01-21 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -2850000 | -2850000 | 0 | 2019-01-01 | Drawdown Register
2019-01-21 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | -5000000 | -5000000 | 0 | 2019-01-01 | Drawdown Register
2019-01-29 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | -4600000 | -4600000 | 0 | 2019-01-01 | Drawdown Register
2019-02-07 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | -10400000 | -10400000 | 0 | 2019-02-01 | Drawdown Register
2019-02-28 | Duma Tau — Kronlein | 3242310 | 0 | 3242310 | 2019-02-01 | Drawdown Register
2019-03-06 | LIH- Nkurenkuru Ph 1 | -1745000 | -1745000 | 0 | 2019-03-01 | Drawdown Register
2019-03-07 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | -4600000 | -4600000 | 0 | 2019-03-01 | Drawdown Register
2019-03-19 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | -6000000 | -6000000 | 0 | 2019-03-01 | Drawdown Register
2019-03-28 | LIH- Nkurenkuru Ph 1 | -1855000 | -1855000 | 0 | 2019-03-01 | Drawdown Register
2019-03-29 | Duma Tau — Kronlein | 4087330 | 0 | 4087330 | 2019-03-01 | Drawdown Register
2019-04-30 | Duma Tau — Kronlein | 1923105 | 0 | 1923105 | 2019-04-01 | Drawdown Register
2019-05-13 | Duma Tau — Kronlein | 679120 | 0 | 679120 | 2019-05-01 | Drawdown Register
2019-05-13 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | -4000000 | -4000000 | 0 | 2019-05-01 | Drawdown Register
2019-05-13 | LIH- Nkurenkuru Ph 1 | 998970.04 | 0 | 998970.04 | 2019-05-01 | Drawdown Register
2019-06-27 | Duma Tau — Kronlein | 2368545 | 0 | 2368545 | 2019-06-01 | Drawdown Register
2019-06-27 | Duma Tau — Kronlein | -3191939.24 | -3191939.24 | 0 | 2019-06-01 | Drawdown Register
2019-06-27 | LIH- Nkurenkuru Ph 1 | -1076405.04 | -1076405.04 | 0 | 2019-06-01 | Drawdown Register
2019-06-27 | LIH- Nkurenkuru Ph 1 | 3048706.28 | 0 | 3048706.28 | 2019-06-01 | Drawdown Register
2019-07-31 | Duma Tau — Kronlein | -2000000 | -2000000 | 0 | 2019-07-01 | Drawdown Register
2019-07-31 | Duma Tau — Kronlein | 450000 | 0 | 450000 | 2019-07-01 | Drawdown Register
2019-07-31 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -1000000 | -1000000 | 0 | 2019-07-01 | Drawdown Register
2019-07-31 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -450000 | -450000 | 0 | 2019-07-01 | Drawdown Register
2019-09-03 | Duma Tau — Kronlein | 450000 | 0 | 450000 | 2019-09-01 | Drawdown Register
2019-09-03 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -450000 | -450000 | 0 | 2019-09-01 | Drawdown Register
2019-09-16 | Duma Tau — Kronlein | 2819720 | 0 | 2819720 | 2019-09-01 | Drawdown Register
2019-09-16 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -3673595 | -3673595 | 0 | 2019-09-01 | Drawdown Register
2019-09-16 | LIH- Nkurenkuru Ph 1 | 853874.94 | 0 | 853874.94 | 2019-09-01 | Drawdown Register
2019-10-14 | Duma Tau — Kronlein | -1917460 | -1917460 | 0 | 2019-10-01 | Drawdown Register
2019-10-14 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | 4000000 | 0 | 4000000 | 2019-10-01 | Drawdown Register
2019-10-14 | LIH- Nkurenkuru Ph 1 | 1945790.17 | 0 | 1945790.17 | 2019-10-01 | Drawdown Register
2019-12-18 | Duma Tau — Kronlein | -1000000 | -1000000 | 0 | 2019-12-01 | Drawdown Register
2019-12-18 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | 38288179.11 | 0 | 38288179.11 | 2019-12-01 | Drawdown Register
2020-01-31 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | 5747034.31 | 0 | 5747034.31 | 2020-01-01 | Drawdown Register
2020-01-31 | LIH- Nkurenkuru Ph 1 | 2480910.01 | 0 | 2480910.01 | 2020-01-01 | Drawdown Register
2020-03-26 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -7000000 | -7000000 | 0 | 2020-03-01 | Drawdown Register
2020-03-26 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | 3169354.38 | 0 | 3169354.38 | 2020-03-01 | Drawdown Register
2020-03-26 | LIH- Nkurenkuru Ph 1 | 1988729.65 | 0 | 1988729.65 | 2020-03-01 | Drawdown Register
2020-03-31 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | 17154800 | 0 | 17154800 | 2020-03-01 | Drawdown Register
2020-09-01 | LIH- Nkurenkuru Ph 1 | 7609365.83 | 0 | 7609365.83 | 2020-09-01 | Drawdown Register
2020-10-14 | LIH- Nkurenkuru Ph 1 | 948648 | 0 | 948648 | 2020-10-01 | Drawdown Register
2021-03-10 | Duma Tau — Kronlein | 3798648.74 | 0 | 3798648.74 | 2021-03-01 | Drawdown Register
2021-03-10 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | 7240475.32 | 0 | 7240475.32 | 2021-03-01 | Drawdown Register
2021-03-10 | LIH- Nkurenkuru Ph 1 | 954998.58 | 0 | 954998.58 | 2021-03-01 | Drawdown Register
2021-04-15 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | 11099288.4 | 0 | 11099288.4 | 2021-04-01 | Drawdown Register
2021-07-08 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | 9000000 | 0 | 9000000 | 2021-07-01 | Drawdown Register
2021-07-08 | LIH- Nkurenkuru Ph 1 | 476082 | 0 | 476082 | 2021-07-01 | Drawdown Register
2021-09-16 | Duma Tau — Kronlein | 1152462.5 | 0 | 1152462.5 | 2021-09-01 | Drawdown Register
2021-09-16 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | 8965058 | 0 | 8965058 | 2021-09-01 | Drawdown Register
2021-11-11 | Duma Tau — Kronlein | 737907.5 | 0 | 737907.5 | 2021-11-01 | Drawdown Register
2021-11-11 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | 6875267.02 | 0 | 6875267.02 | 2021-11-01 | Drawdown Register
2021-12-21 | Duma Tau — Kronlein | 3481490.1 | 0 | 3481490.1 | 2021-12-01 | Drawdown Register
2021-12-21 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | 1093777.66 | 0 | 1093777.66 | 2021-12-01 | Drawdown Register
2022-05-27 | Lithon Developers - Nkurenkuru Ext 2 | -5500000 | -5500000 | 0 | 2022-05-01 | Drawdown Register
2022-08-31 | NIC - Otjomuise Ext 10 | -7000000 | -7000000 | 0 | 2022-08-01 | Drawdown Register
2023-04-27 | Duma Tau — Kronlein | 694476.87 | 0 | 694476.87 | 2023-04-01 | Drawdown Register
2023-04-27 | NIC - Otjomuise Ext 10 | 6288799.39 | 0 | 6288799.39 | 2023-04-01 | Drawdown Register
2023-06-12 | Duma Tau — Kronlein | 451182.19 | 0 | 451182.19 | 2023-06-01 | Drawdown Register
2023-06-12 | NIC - Otjomuise Ext 10 | 1064625.1 | 0 | 1064625.1 | 2023-06-01 | Drawdown Register
2023-08-22 | Damask Dunescape Villas | -6000000 | -6000000 | 0 | 2023-08-01 | Drawdown Register
2023-10-25 | Mossy Wood Notes Investments- Turnstone Villas | -2500000 | -2500000 | 0 | 2023-10-01 | Drawdown Register
2023-11-07 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -4675000 | -4675000 | 0 | 2023-11-01 | Drawdown Register
2024-03-18 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -5000000 | -5000000 | 0 | 2024-03-01 | Drawdown Register
2024-06-20 | Damask Dunescape Villas | -3600000 | -3600000 | 0 | 2024-06-01 | Drawdown Register
2024-08-09 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -8000000 | -8000000 | 0 | 2024-08-01 | Drawdown Register
2024-09-27 | Damask Dunescape Villas | -9751000 | -9751000 | 0 | 2024-09-01 | Drawdown Register
2024-11-20 | Mossy Wood Notes Investments- Turnstone Villas | -500000 | -500000 | 0 | 2024-11-01 | Drawdown Register
2024-11-29 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -6913000 | -6913000 | 0 | 2024-11-01 | Drawdown Register
2024-12-12 | Damask Dunescape Villas | -4700000 | -4700000 | 0 | 2024-12-01 | Drawdown Register
2024-12-19 | PAM Tree Investment Pty Ltd - Kuisebmund Erf 5758 | -13500000 | -13500000 | 0 | 2024-12-01 | Drawdown Register
2025-02-10 | Damask Dunescape Villas | -1500000 | -1500000 | 0 | 2025-02-01 | Drawdown Register
2025-02-26 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -8600000 | -8600000 | 0 | 2025-02-01 | Drawdown Register
2025-04-01 | Mossy Wood Notes Investments- Turnstone Villas | -3640000 | -3640000 | 0 | 2025-04-01 | Drawdown Register
2025-07-01 | Mossy Wood Notes Investments- Turnstone Villas | -7400000 | -7400000 | 0 | 2025-07-01 | Drawdown Register
2025-08-12 | Damask- Mondesa Palms | -7000000 | -7000000 | 0 | 2025-08-01 | Drawdown Register
2025-08-12 | Blue Mont Pty Ltd The Ridge | -13000000 | -13000000 | 0 | 2025-08-01 | Drawdown Register
2025-09-23 | Damask Dunescape Villas | 24000000 | 0 | 24000000 | 2025-09-01 | Drawdown Register
2025-09-29 | Mango Cove - Otjomuise Ext 10 | -12000000 | -12000000 | 0 | 2025-09-01 | Drawdown Register
2025-10-07 | Mossy Wood Notes Investments- Turnstone Villas | -2260000 | -2260000 | 0 | 2025-10-01 | Drawdown Register
2025-11-27 | PAM Tree Investment Pty Ltd - Kuisebmund Erf 5758 | -10750000 | -10750000 | 0 | 2025-11-01 | Drawdown Register
2026-03-12 | PAM Tree Investment Pty Ltd - Kuisebmund Erf 5758 | -13600000 | -13600000 | 0 | 2026-03-01 | Drawdown Register
2026-05-29 | Block 9 - C-Breeze Heights | -1209348.2 | -1209348.2 | 0 | 2026-05-01 | C-Breeze Inputs
2026-06-01 | Damask- Mondesa Palms | -8000000 | -8000000 | 0 | 2026-06-01 | Drawdown Register
2026-06-04 | Block 9 - C-Breeze Heights | -1959878.2 | -1959878.2 | 0 | 2026-06-01 | C-Breeze Inputs
2026-06-26 | Block 9 - C-Breeze Heights | -1219884.74 | -1219884.74 | 0 | 2026-06-01 | C-Breeze Inputs
2026-07-01 | PAM Tree Investment Pty Ltd - Kuisebmund Erf 5758 | -3000000 | -3000000 | 0 | 2026-07-01 | Drawdown Register
2026-07-28 | Block 9- Tama Estates | -4466720.46 | -4466720.46 | 0 | 2026-07-01 | Tama Inputs — Claim 1
2026-07-29 | PAM Tree Investment Pty Ltd - Kuisebmund Erf 5758 | -4150000 | -4150000 | 0 | 2026-07-01 | Drawdown Register
2026-08-18 | Blue Mont Pty Ltd The Ridge | -7000000 | -7000000 | 0 | 2026-08-01 | Drawdown Register
|  |  | -371004230.88 | 207800002.09
| TOTAL | -163204228.79 | -742008461.76 | 415600004.18
PROJECT SUMMARY — TOTAL DRAWDOWNS & DISTRIBUTIONS
Project | Total Drawdown (N$) | Total Distribution (N$)
Erf 1470 Khomasdal | 0 | 0
Dunescape Villas (Erf 5159) | 0 | 0
PAM Tree (Erf 5758) | 0 | 0
Turnstone Villas (Erf 8939) | 0 | 0
Lithon Nkurenkuru Ext 2 | 0 | 0
Mondesa Palms | 0 | 0
The Ridge — Rocky Crest Ext 4 | 0 | 0
Mango Cove (Otjomuise Ext 10) | 0 | 0
C-Breeze Heights | 0 | 0
Tama Estates | 0 | 0
Duma Tau — Kronlein | -36109399.24 | 42507267.9
LIH Nkurenkuru Ph 1 | 0 | 0
NIC Otjomuise Ext 10 (Erf 5221) | 0 | 0
Heavens Ark — Otjomuise | 0 | 0
TOTAL | -36109399.24 | 42507267.9
-36109399.24
Formulas:
Month key = DATE(YEAR([Date]),MONTH([Date]),1)

## Notes & Reconciliations
SOURCES, ASSUMPTIONS AND OPEN RECONCILIATIONS
Read this before the numbers go into a GIPF pack. Items marked OPEN are unresolved differences between two documents in the folder; neither has been overridden.
# | Item | Status | Detail
1 | Treatment of Tama Estates and C-Breeze Heights | APPLIED | Per instruction, the 'Equity - Investor' line in the Tama Estates Vert Development Model (N$10,100,000 committed, 20.8% IRR, 1.32x EMx, distributions N$13,341,540) and the 'Equity - Mezzanine' line in the C-Breeze Heights Vert Development Model (N$1,994,992, 18.0% IRR, 1.15x EMx, distributions N$2,428,302) are treated as the fund's own returns. Note the labels in the models are 'Equity - Investor' and 'Equity - Mezzanine' respectively, not both as given.
2 | C-Breeze equity line vs the KAHF facility | OPEN | The Vert model carries Equity-Mezzanine of N$1,994,992. The signed KAHF facility is N$5,000,000 and N$4,389,111 has actually been drawn (29-May, 04-Jun and 26-Jun 2026). The Vert model is dated 05-03-2026 and pre-dates the drawdowns. Sheet 2 uses the drawn capital for cash and the Vert model's 18.0% for IRR, per instruction. The model should be re-run on the N$5m facility.
3 | Fund drawdown register total rows are stale | OPEN | In the fund drawdown register (Drawdowns tab), row 113 'Total Drawdowns' sums only columns B, C, D, E, F, G, I and O — it omits Dunescape, Turnstone, PAM Tree, Mondesa, Rocky Crest and Mango Cove entirely. Row 114 'Total Distributions' likewise omits the N$24.0m Dunescape repayment. The stated totals of N$243,535,135 and N$183,800,002 are therefore both understated. This workbook re-sums the register line by line: N$368,755,917 deployed and N$267,283,868 received.
4 | Erf 1470 Khomasdal — capital advanced | OPEN | The fund register carries N$96,688,000 of drawdowns; the project workbook's own notice register carries N$95,611,595. The difference is exactly N$1,076,405.04, a 27-Jun-2019 entry present in the register and absent from the project ledger.
5 | Duma Tau — register vs project ledger | OPEN | Register: N$36,109,399 out / N$42,507,268 in. Project workbook: N$38,910,481 out / N$42,162,690 in. The workbook itself flags both differences (facility over-advanced by N$10,910,481; register basis differs by N$827,119). Sheet 4 follows the register because it is the only dated source; Sheet 2's IRR follows the project workbook.
6 | Heavens Ark — register nets recycled capital | OPEN | Register: N$65,000,000 out / N$75,599,843 in. Project workbook: N$80,000,936 out / N$90,600,779 in. The N$15,000,936 difference is the Aug-2019 recycle, netted in the register and shown gross in the workbook. Net profit is N$10,599,843 on both bases.
7 | Mango Cove — two irreconcilable positions | OPEN | The fund register and the KAHF Projects schedule both show N$12,000,000 advanced on 29-Sep-2025 against a N$20,000,000 approval. The interest schedule ('C - Otjimuise Ext 10, Margo Cov') shows a separate N$15,000,000 facility granted 01-May-2026 at 14% NACM with only N$5,028,879 drawn and a balance of N$5,108,318 at 31-Jul-2026. This workbook uses N$12,000,000. Resolve before the pack goes out.
8 | Mondesa Palms — the model is provisional | OPEN | The Mondesa model's own dashboard states that no facility agreement, drawdown notice or investment approval was supplied, and that facility size, interest rate, first drawdown date, drawn-to-date and unit selling price are all placeholders. Its 18.94% IRR is therefore provisional. The register shows N$15,000,000 drawn (Aug-25 and Jun-26); the KAHF Projects schedule shows N$12,958,884; the model assumes N$11,365,558.
9 | Mondesa Palms — scope | OPEN | The hardcoded plan is 134 units across 3 erven (4420 / 4421 / 4422). The only model in the folder covers Erf 4420 and 40 units. The KAHF Projects schedule shows 131. No model exists for the other two erven.
10 | The Ridge — Rocky Crest unit count | OPEN | Hardcoded plan is 38 units. The KAHF Projects schedule shows 40 at 30-Sep-2027 and 108 extended. The financial model does not state a unit count at all.
11 | PAM Tree — return dashboard is broken | OPEN | Two PAM Tree workbooks exist. 'PAM Tree/KAHF_PAM Tree Performance.xlsx' contains Turnstone Villas data, not PAM Tree data — its ledger shows the N$16.3m / N$18.97m Turnstone figures. 'Lithon Nkurenkuru Ext 2/KAHF_PAM Tree Performance(CHQ).xlsx' has the correct N$45m ledger but its dashboard returns a REF error and its total row mis-sums to a -33.5% IRR. Sheet 2 uses the 24% reported on Contract Parameters D31.
12 | Turnstone Villas — negative realised IRR | NOTED | The -10.6% on Sheet 2 is the workbook's own realised XIRR, which deliberately excludes the N$21.3m residual value. On a total-value basis the project returns 2.16x. Present both, or the number reads as a loss.
13 | Dunescape IRR includes fees | NOTED | The 36.03% is computed in the workbook over loan cash flows plus a N$7,177,927 project management fee and an N$8,508,452 NAV. The workbook notes the fund's return here is fee-based, not interest-based.
14 | Trial balance dates | OPEN | Two fund trial balances appear in the pack. The one inside the project performance workbooks is dated 28-02-2026 (GIPF N$151,835,312.42, comparative N$108,341,357). The one in the July-2026 interest schedule is dated 28-02-2025 and shows GIPF N$131,984,039. The N$108,341,357 and N$131,984,039 figures are both presented as 28-02-2025.
15 | Distributions to GIPF | NOTED | No cash distribution from KAHF to GIPF is recorded anywhere in the folder. Sheet 1 shows nil. If distributions have been paid, the evidence is outside this pack.
16 | Ledger reconciles to the fund register | NOTED | The register alone (Drawdowns rows 25-99, columns B:O) totals -350,998,399.28 out and +207,800,002.09 in. This model's ledger totals -368,755,917.02 and +267,283,868.44. The bridge is exact: replace the register's single -5,500,000 Lithon line with the revolving schedule's actual -10,251,686.14 / +10,887,250.93; add the post-June-2026 events the register has not yet picked up (PAM Tree -4,150,000 drawn and +34,396,615.42 repaid, Turnstone +14,000,000); and add C-Breeze (-4,389,111.14) and Tama (-4,466,720.46) with their N$100,000 upfront fees, neither of which the register carries.
17 | Basis of the monthly ledger | NOTED | Sheet 4 is built from the fund drawdown register (the only source with dated fund-level flows for every project), extended with post-June-2026 events from the project ledgers, the Lithon revolving schedule in place of the register's single net line, and the C-Breeze and Tama drawdown tables. One register date, '01/06/2025 - Mondesa' N$8,000,000, sits after the March-2026 entries and has been read as 01-06-2026.
18 | Lithon reports two different realised returns | OPEN | Historical Ledgers D110 computes a cash-only realised XIRR of 15.76%. The Return Dashboard C8 shows 16.08%, but that cell is labelled 'Effective Annual Rate (15% NACM)' — it is the coupon's effective rate, not a return measure. Independent recomputation of the dated flows gives 15.76%, confirming D110.
19 | Khomasdal repayments stated three ways | OPEN | Return Dashboard C4 'Sales Repayments' = N$38,821,977.50; Historical Ledgers R25 'Total Realized Distributions' = N$37,033,391; R27 = N$39,236,076.75. This model uses R25, which is the figure the dated notice register sums to. The dashboard's Money Multiple C7 (-0.406) is also sign-broken.
20 | KAHF Projects schedule — unit total double-counts | NOTED | In 'KAHF Projects .xlsx', the seven project unit rows B20:B26 sum to 609, which is what B27 correctly shows. B38 'Total' reads 1,218 — exactly twice that. Do not quote 1,218.
21 | Dashboard sign conventions differ | NOTED | 'Gross Money Paid (Outflows)' is positive on the Duma Tau dashboard (+38,910,480.75) and negative on LIH, Heavens Ark and Mossy Wood. This model normalises everything to outflow-negative.
22 | Valuation dates are not uniform | NOTED | Carrying values on Sheet 2 are as at: Khomasdal 28-02-26, Dunescape 28-02-26, Lithon 31-07-26, Turnstone 31-07-26, Duma Tau and LIH at close-out, and cost for Mondesa, Rocky Crest and Mango Cove. A single valuation date would need fresh valuations.

## 5. Cash IRR & Residual
SHEET 5 — FUND-LEVEL CASH IRR & RESIDUAL, AS AT 30 SEPTEMBER 2026
Methodology: XIRR over every dated fund-level cash flow on the Ledger tab (capital deployed negative, distributions received positive), plus one terminal cash flow dated 30-Sep-2026 equal to the portfolio's carrying value (NAV) — the same 'XIRR incl. NAV' approach used per-project on Sheet 2, column L. Rebuilt to match the Ledger 1:1 after restructuring; rows below link live to Ledger!A5:C112.
A. DATED FUND CASH FLOWS (LINKED TO LEDGER)
Date | Project | Cash flow (N$) | Erf 1470 Khomasdal Net | Excluding Erf 1470 Khomasdal
2017-11-28 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -45500000 | 0 | -45500000
2017-11-28 | LIH- Nkurenkuru Ph 1 | -2200000 | 0 | -2200000
2018-03-09 | Duma Tau — Kronlein | -22000000 | 0 | -22000000
2018-04-26 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | -10000000 | 0 | -10000000
2018-06-29 | LIH- Nkurenkuru Ph 1 | -700000 | 0 | -700000
2018-07-23 | LIH- Nkurenkuru Ph 1 | -4300000 | 0 | -4300000
2018-08-10 | Duma Tau — Kronlein | -6000000 | 0 | -6000000
2018-08-10 | LIH- Nkurenkuru Ph 1 | -5000000 | 0 | -5000000
2018-09-13 | Duma Tau — Kronlein | 1302000 | 0 | 1302000
2018-09-19 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -1500000 | 0 | -1500000
2018-09-19 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | -1000000 | 0 | -1000000
2018-10-11 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | -10000000 | 0 | -10000000
2018-11-22 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | -9400000 | 0 | -9400000
2018-11-29 | LIH- Nkurenkuru Ph 1 | -2200000 | 0 | -2200000
2018-12-14 | Duma Tau — Kronlein | 10443745 | 0 | 10443745
2019-01-11 | Duma Tau — Kronlein | 4425225 | 0 | 4425225
2019-01-21 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -2850000 | 0 | -2850000
2019-01-21 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | -5000000 | 0 | -5000000
2019-01-29 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | -4600000 | 0 | -4600000
2019-02-07 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | -10400000 | 0 | -10400000
2019-02-28 | Duma Tau — Kronlein | 3242310 | 0 | 3242310
2019-03-06 | LIH- Nkurenkuru Ph 1 | -1745000 | 0 | -1745000
2019-03-07 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | -4600000 | 0 | -4600000
2019-03-19 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | -6000000 | 0 | -6000000
2019-03-28 | LIH- Nkurenkuru Ph 1 | -1855000 | 0 | -1855000
2019-03-29 | Duma Tau — Kronlein | 4087330 | 0 | 4087330
2019-04-30 | Duma Tau — Kronlein | 1923105 | 0 | 1923105
2019-05-13 | Duma Tau — Kronlein | 679120 | 0 | 679120
2019-05-13 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | -4000000 | 0 | -4000000
2019-05-13 | LIH- Nkurenkuru Ph 1 | 998970.04 | 0 | 998970.04
2019-06-27 | Duma Tau — Kronlein | 2368545 | 0 | 2368545
2019-06-27 | Duma Tau — Kronlein | -3191939.24 | 0 | -3191939.24
2019-06-27 | LIH- Nkurenkuru Ph 1 | -1076405.04 | 0 | -1076405.04
2019-06-27 | LIH- Nkurenkuru Ph 1 | 3048706.28 | 0 | 3048706.28
2019-07-31 | Duma Tau — Kronlein | -2000000 | 0 | -2000000
2019-07-31 | Duma Tau — Kronlein | 450000 | 0 | 450000
2019-07-31 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -1000000 | 0 | -1000000
2019-07-31 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -450000 | 0 | -450000
2019-09-03 | Duma Tau — Kronlein | 450000 | 0 | 450000
2019-09-03 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -450000 | 0 | -450000
2019-09-16 | Duma Tau — Kronlein | 2819720 | 0 | 2819720
2019-09-16 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -3673595 | 0 | -3673595
2019-09-16 | LIH- Nkurenkuru Ph 1 | 853874.94 | 0 | 853874.94
2019-10-14 | Duma Tau — Kronlein | -1917460 | 0 | -1917460
2019-10-14 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | 4000000 | 0 | 4000000
2019-10-14 | LIH- Nkurenkuru Ph 1 | 1945790.17 | 0 | 1945790.17
2019-12-18 | Duma Tau — Kronlein | -1000000 | 0 | -1000000
2019-12-18 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | 38288179.11 | 0 | 38288179.11
2020-01-31 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | 5747034.31 | 0 | 5747034.31
2020-01-31 | LIH- Nkurenkuru Ph 1 | 2480910.01 | 0 | 2480910.01
2020-03-26 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -7000000 | 0 | -7000000
2020-03-26 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | 3169354.38 | 0 | 3169354.38
2020-03-26 | LIH- Nkurenkuru Ph 1 | 1988729.65 | 0 | 1988729.65
2020-03-31 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | 17154800 | 0 | 17154800
2020-09-01 | LIH- Nkurenkuru Ph 1 | 7609365.83 | 0 | 7609365.83
2020-10-14 | LIH- Nkurenkuru Ph 1 | 948648 | 0 | 948648
2021-03-10 | Duma Tau — Kronlein | 3798648.74 | 0 | 3798648.74
2021-03-10 | MPG _ Heaven's Ark — Otjomuise Lifestyle Estate | 7240475.32 | 0 | 7240475.32
2021-03-10 | LIH- Nkurenkuru Ph 1 | 954998.58 | 0 | 954998.58
2021-04-15 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | 11099288.4 | 0 | 11099288.4
2021-07-08 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | 9000000 | 0 | 9000000
2021-07-08 | LIH- Nkurenkuru Ph 1 | 476082 | 0 | 476082
2021-09-16 | Duma Tau — Kronlein | 1152462.5 | 0 | 1152462.5
2021-09-16 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | 8965058 | 0 | 8965058
2021-11-11 | Duma Tau — Kronlein | 737907.5 | 0 | 737907.5
2021-11-11 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | 6875267.02 | 0 | 6875267.02
2021-12-21 | Duma Tau — Kronlein | 3481490.1 | 0 | 3481490.1
2021-12-21 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | 1093777.66 | 0 | 1093777.66
2022-05-27 | Lithon Developers - Nkurenkuru Ext 2 | -5500000 | 0 | -5500000
2022-08-31 | NIC - Otjomuise Ext 10 | -7000000 | 0 | -7000000
2023-04-27 | Duma Tau — Kronlein | 694476.87 | 0 | 694476.87
2023-04-27 | NIC - Otjomuise Ext 10 | 6288799.39 | 0 | 6288799.39
2023-06-12 | Duma Tau — Kronlein | 451182.19 | 0 | 451182.19
2023-06-12 | NIC - Otjomuise Ext 10 | 1064625.1 | 0 | 1064625.1
2023-08-22 | Damask Dunescape Villas | -6000000 | 0 | -6000000
2023-10-25 | Mossy Wood Notes Investments- Turnstone Villas | -2500000 | 0 | -2500000
2023-11-07 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -4675000 | 0 | -4675000
2024-03-18 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -5000000 | 0 | -5000000
2024-06-20 | Damask Dunescape Villas | -3600000 | 0 | -3600000
2024-08-09 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -8000000 | 0 | -8000000
2024-09-27 | Damask Dunescape Villas | -9751000 | 0 | -9751000
2024-11-20 | Mossy Wood Notes Investments- Turnstone Villas | -500000 | 0 | -500000
2024-11-29 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -6913000 | 0 | -6913000
2024-12-12 | Damask Dunescape Villas | -4700000 | 0 | -4700000
2024-12-19 | PAM Tree Investment Pty Ltd - Kuisebmund Erf 5758 | -13500000 | 0 | -13500000
2025-02-10 | Damask Dunescape Villas | -1500000 | 0 | -1500000
2025-02-26 | Aromatic Fresh Notes Investments Pty Ltd - Erf 1470 Khomasdal | -8600000 | 0 | -8600000
2025-04-01 | Mossy Wood Notes Investments- Turnstone Villas | -3640000 | 0 | -3640000
2025-07-01 | Mossy Wood Notes Investments- Turnstone Villas | -7400000 | 0 | -7400000
2025-08-12 | Damask- Mondesa Palms | -7000000 | 0 | -7000000
2025-08-12 | Blue Mont Pty Ltd The Ridge | -13000000 | 0 | -13000000
2025-09-23 | Damask Dunescape Villas | 24000000 | 0 | 24000000
2025-09-29 | Mango Cove - Otjomuise Ext 10 | -12000000 | 0 | -12000000
2025-10-07 | Mossy Wood Notes Investments- Turnstone Villas | -2260000 | 0 | -2260000
2025-11-27 | PAM Tree Investment Pty Ltd - Kuisebmund Erf 5758 | -10750000 | 0 | -10750000
2026-03-12 | PAM Tree Investment Pty Ltd - Kuisebmund Erf 5758 | -13600000 | 0 | -13600000
2026-05-29 | Block 9 - C-Breeze Heights | -1209348.2 | 0 | -1209348.2
2026-06-01 | Damask- Mondesa Palms | -8000000 | 0 | -8000000
2026-06-04 | Block 9 - C-Breeze Heights | -1959878.2 | 0 | -1959878.2
2026-06-26 | Block 9 - C-Breeze Heights | -1219884.74 | 0 | -1219884.74
2026-07-01 | PAM Tree Investment Pty Ltd - Kuisebmund Erf 5758 | -3000000 | 0 | -3000000
2026-07-28 | Block 9- Tama Estates | -4466720.46 | 0 | -4466720.46
2026-07-29 | PAM Tree Investment Pty Ltd - Kuisebmund Erf 5758 | -4150000 | 0 | -4150000
2026-08-18 | Blue Mont Pty Ltd The Ridge | -7000000 | 0 | -7000000
2026-08-30 | Revaluation : Profit Adjustment | 0 | 0 | 0
2026-07-30 | RESIDUAL — portfolio carrying value (NAV), terminal cash flow | 184102954.74 | 0 | 184102954.74
| TOTAL (incl. residual) | 20898725.95
B. CASH IRR & RESIDUAL — RESULTS
Cash IRR, inception to 30-Sep-2026 (incl. residual) |  | 3.242%
Residual / NAV excluding Khomasdal Erf 1470 |  | 16.93%
TVPI | 1.0563
DPI | 0.5601
RVPI | 0.49623
MOIC | 1.0563

## Statement_of_Cash_F_-_July_2026
Statement of Cash Flows
Konigstein Affordable Housing Fund
For the 3 Months ended 31 July 2026
Account | 3 MONTHS ENDED | YEAR ENDED
| 2026-07-31 | 2025-12-31
Operating Activities
Payments to suppliers and employees | -380249.58 | -4695005
Interest Received |  | 1580113
Net Cash Flows from Operating Activities | -380249.58 | -3114892
Investing Activities
Erf 1470 Khomasdal | -500000 | 8902639.41
Nkurenkulu Ext 2-Phase 2-Lithon | 0 | -78279.71
Dunescape Villas-Swakopmund | -5900000 | 20520366.18
Turnstone | 0 | -13968610.25
PAM Tree | 3262978.09 | -23328666.16
Rocky Crest Windhoek-Blue Mont | 0 | 0
Block 9-Swakopmund | -4389111.14
Otjomuise Ext 10-Margo Cove | -4888879.26
Net Cash Flows from Investing Activities | -12415012.31 | -7952550.53
Financing Activities
Other cash items from financing activities
Capital Drawdowns/(Distributions) | 23000000 | 35632938.42
Net Cash Flows from Financing Activities | 23000000 | 35632938.42
Net Cash Flows | 10204738.11 | 24565495.89
Cash and Cash Equivalents
Cash and cash equivalents at beginning of period | 56832420.6 | 11258687.3
Net change in cash for period | 10204738.11 | 24046053.98
Cash and cash equivalents at end of period | 67037158.71 | 35304741.28

## Profit_and_Loss_Jul_2026
Detailed Income Statement
Konigstein Affordable Housing Fund
For the 3 Months ended 31 July 2026
Account | 3 MONTHS ENDED | YEAR ENDED
| 2026-07-31 | 2025-12-31
Revenue
Erf 1470 Khomasdal | 468506.7 | 16724749.07
Nkurenkulu Ext 2-Phase 2-Lithon | 62481.84 | 365629.4
Dunescape Villas-Swakopmund | 0 | 2427143.3
Turnstone | 0 | 939942.93
Block 9-CBreeze Swakopmund | 1192.78
Otjomuise Ext 10-Mago Cove | 81603.09
PAM TREE-Kuisebmund | 745978.88
Total Revenue | 1359763.29 | 20457464.7
Operating Expenses
Administrative Expenses
Accounting Fees | 4772.5 | 60978
Bank Charges | 1805.02 | 3617.7
Management Fee | 1247896.05 | 6401193.81
Total Administrative Expenses | 1254473.57 | 6465789.51
Other Expenses
Trustee Fees | 34597 | 88274.38
Meeting Expenses | 0 | 3920
Consulting Fees | 0 | 12075
Legal Fees | 0 | 16560
Audit Fees | 460391.91 | 282712.55
NCCC Committee member Sitting fees | 2152.5 | 13125
Transaction Expense | 2444.05 | 62359.18
Total Other Expenses | 499585.46 | 479026.11
Profit/(Loss)from Opperating Expenses | -394295.74 | 13512649.08
Finance Income
Interest Received from Cash and Cash Equivalent | 1128175.3 | 1580113
Net Profit/ (Loss) | 733879.56 | 15092762.08

## Balance_Sheet_July_2026
Statement of Financial Position
Konigstein Affordable Housing Fund
As at 31 July 2026
| Account | 2026-07-31 | 2025-12-31
Assets |  |  |  | Net Profit
Fixed Assets
| Erf 1470 Khomasdal | 40105520.93 | 51356035
| Nkurenkuru Extension 2 -Phase 2 | 1037365.93 | 875383.15
| Dunescape Villas- Mondessa Swakopmund | 12958883.82 | 5069869
| Turnstone Villas-Mossy wood | 4911827.71 | 17247230
| PAM TREE | 35672548.44 | 23328666.16
| Rocky Chrest Windhoek-Blue Mont | 13022185.55 | 0
| Block 9 - Swakopmund | 4290303.92 | 0
| Otjomuise Ext 10 - Margo Cove | 4827159.73 | 0
Total Fixed Assets |  | 116825796.03 | 97877183.31
Current Assets
| Cash and Cash Equivalent | 67037158.71 | 35754741
| Accounts Receivable | 240000 | 0
Total Current Assets |  | 67277158.71 | 35754741
Total Assets |  | 184102954.74 | 133631924.31
Equity
| Capital Account: GIPF | 188072936.42 | 138964025.42
| Capital Account: Konigstein Capital | 1880750 | 1389661
| Current Year Earnings | 1201303.24 | 0
| Retained Income | -7294346.45 | -6721762
Total Equity+ Liability |  | 184102954.74 | 133631924.42
Liabilities
| Accounts Payable | 242311.53 | 0
Total Current Liabilities |  | 242311.53 | 0
Net Assets |  | 183860643.21 | 133631924.31
Source: Konigstein Affordable Housing Fund - Balance Sheet as at 31 July 2026 (uploaded file), uploaded 7 September 2026